Goat OS Mobile

Feature Action Flows & Delivery Roadmap

Prepared: Monday, 27 July 2026 Review gate: Thursday, 30 July 2026 — engine + Birth, Death, Shifting, Feed Transport Slice complete: Thursday, 6 August 2026 — Colostrum, Milk Preparation, Health Basis: Live Slack/Sheets workflow workbook, read 27 July 2026 (10,891 production action rows) Audience: Product, Operations, Engineering, SOP/Clinical

# 1.  Summary

The review asks for two things: change three workflows already in the app (Birth, Death, Shifting), and build four new pages (Milk Preparation, Health, Feed Transport, Colostrum Feeding).

All seven already run in production today — but in a Slack and Google Sheets automation, not in Goat OS. The workbook behind that automation is not a wishlist. It is the live system, with real operators, real volumes, and a real workflow engine. This document reads that engine and states the exact action flow for each task.

The single most important finding The legacy system is not seven separate features. It is one generic task-and-action engine driven by configuration, with seven configurations loaded into it. Goat OS has no equivalent engine — the module that would hold it is currently an empty file. Building seven bespoke screens would be the wrong answer and would not survive the eighth workflow.

## What this changes about the deadline

Delivering all seven by Thursday 30 July is not achievable, because six of the seven depend on an engine that does not exist yet. Rather than plan a date that cannot hold, the work is split into two gates:

Thursday 30 July — build the engine and land the three reworks plus a straight port of Feed Transport. Four workflows demonstrable on a device.

Thursday 6 August — the three remaining pages, which carry the heavy clinical and milk protocols.

## Four findings that change the plan

| # | Finding | Consequence |
| --- | --- | --- |
| 1 | The engine does not exist. The task module is a single placeholder file; the health module is an empty marker. | Six of seven features are blocked on it. It is the critical path and must be built first. |
| 2 | Death's open question is already answered. Production shows 59 death videos and 59 post-mortem videos — exactly 1:1, with no condition. | Post-mortem video is unconditional. Treat as confirmed by evidence, pending clinical sign-off. |
| 3 | Colostrum is not a fixed 4-session checklist. Real cases run to an 11th attempt, plus a separate "Morning Colostrum". | Any design assuming a fixed session count is wrong against production data. |
| 4 | Feed Transport has almost no production signal — 2 action rows in total, one template step. | Porting it takes hours. Designing a real dispatch/receipt flow is net-new product work. |

# 2.  Where Goat OS stands today

Volumes are actual action rows in the live workbook, and are the best available measure of how heavily each workflow is used.

| Feature | Live volume | In Goat OS backend | In the Android app | Verdict |
| --- | --- | --- | --- | --- |
| Birth | 4,033 | Counts module | Combined Birth/Death screen | Rework — one form, no action chain |
| Milk Preparation | 3,848 | None | None | Build |
| Shifting | 2,581 | Counts + Verification | Shifting, Execute, Pending screens | Rework — closest to target |
| Health (Milk Refusal SOP) | 205 | Empty placeholder | None | Build |
| Death | 118 | Counts module | Combined Birth/Death screen | Rework |
| Feed Transport | 2 | Feed / Inventory | Feed Direction, Packing | Build (port) |
| Colostrum Feeding | inside Birth | None | None | Build |

Good news on Shifting Shifting already has the right shape. The verification gate landed last week: the operator completes with a mandatory video, the move goes to pending verification, and animals relocate only when a verifier approves. That is exactly the pattern the other six need — so it becomes the reference implementation rather than a rebuild.

# 3.  How the workflows are actually structured

Three tables define everything in the live system. "Each task has actions" is literally the production schema:

Workflow Type  (the template — what steps this kind of task has)   →   Workflow  (one real event)   →   Actions  (the ordered steps)

## The eight action types

These eight types carry all 10,891 production rows. This is the vocabulary the Goat OS engine has to support.

| Action type | Volume | What the operator sees | How it completes |
| --- | --- | --- | --- |
| ACTION | 4,170 | An instruction, plus upload a video or photo | Proof uploaded |
| QUESTION | 2,710 | A question — yes/no or free text | Answer recorded |
| MODAL_FORM | 1,436 | A multi-field structured form | Form submitted |
| ACTION_AUTO_VIDEO | 928 | Auto-scheduled step that still needs a video | Proof uploaded |
| ACTION_AUTO | 693 | Nothing — the system completes it | Auto-completed |
| TRIGGER_EVENT | 515 | Nothing — it spawns another workflow | Child workflow created |
| APPROVAL | 255 | Approver reviews and approves or rejects | Verdict recorded |
| QUESTION_SELECT | 184 | Pick from a configured option list | Selection recorded |

## Actions are scheduled, and conditional

Two details make this more than a checklist, and they drive most of the engineering effort:

Scheduling — Steps are not all due at once. Real rules in use include "1 hour after the event", "2 days after at 07:00", "9 days after", and fixed next-day slots at 08:00, 12:00, 16:00 and 21:00.

Conditions — Some steps only exist under certain conditions — and critically, some conditions depend on the answer to an earlier step. Answering "temperature below 100°F" switches the whole flow onto an emergency protocol. A static checklist screen cannot express this.

Every action also carries its own scheduled time, actual time, status, response, video link, uploader, verifier, verification status and remarks. Live status split: 8,631 completed, 1,704 scheduled, 322 posted, 135 skipped, 99 cancelled. Skipped and cancelled are first-class — cancelling a task closes its open steps but never rewrites completed history.

# 4.  Action flow for each feature

Each flow below is the actual production sequence read from the workbook, with the Goat OS change called out.

## 4.1   Birth  —  rework

Highest-volume workflow in the system (4,033 actions). It is not one form — it is three parallel tracks plus a colostrum series.

### Track A — the Mother

| # | Type | Action | When | Detail |
| --- | --- | --- | --- | --- |
| 1 | QUESTION | Are there any babies still inside? | immediately |  |
| 2 | QUESTION | Is the mother licking her babies? | immediately |  |
| 3 | ACTION | Mother's Medicine | immediately | Chocolate Injection 1.5 ml SQ; Meloxicam Paracetamol 4 ml IM; Exapar 20 ml; Glucoboost 100 ml + 150 g concentrate |
| 4 | ACTION | Give ORS water | immediately |  |
| 5 | QUESTION | Is the mother eating? | immediately |  |
| 6 | ACTION | Give ORS water (second) | rule-based |  |
| 7 | TRIGGER_EVENT | Create Shifting Request | +2 days | K0 → Mother shed |

### Track B — each Kid

| # | Type | Action | When | Detail |
| --- | --- | --- | --- | --- |
| 1 | QUESTION | Is the kid clean? (If not, wipe with a towel.) | immediately |  |
| 2 | ACTION | Iodine dipping of umbilical cord | immediately |  |
| 3 | QUESTION | Are the front teeth outside the lower gum? | immediately |  |
| 4 | QUESTION | Is the kid able to suck when you put a finger in its mouth? | immediately |  |
| 5 | QUESTION | 1st Colostrum | immediately | If suck reflex is absent, collect colostrum with a 10 ml syringe and give at least 100 ml. The video must first show the udder contains milk. Follow with 100 ml milk. |
| 6 | QUESTION_SELECT | Take weight of kid | immediately |  |
| 7 | QUESTION | Is the kid standing? | +1 hour |  |
| 8 | ACTION | Tag the kid | +2 days, 07:00 |  |
| 9 | TRIGGER_EVENT | Create Shifting Request | +2 days | K0 → K1 |
| 10 | TRIGGER_EVENT | Create Shifting Request | +9 days | K1 → K2 |

Track C — Abortion is a separate workflow type with four steps: babies still inside? → Mother's Medicine → ORS water → is the mother eating? No kid track and no colostrum.

What changes:  today this is a one-shot form. It becomes a task with a live action list — separate mother and per-kid tracks, scheduled follow-ups at +1 hour, +2 days and +9 days, and two automatic shifting requests. The breed picker shipped last week stays, but becomes one input inside the flow rather than the whole interaction.

## 4.2   Death  —  rework

| # | Type | Action | Detail |
| --- | --- | --- | --- |
| 1 | ACTION | Upload death video | Please upload video with the timestamp |
| 2 | ACTION | Upload post mortem video | Please upload video with the timestamp |

This answers an open review question Post-mortem video is unconditional. Production shows 59 death videos and 59 post-mortem videos — exactly 1:1, with no condition and no cause-based branch. The earlier draft listed "is post-mortem always required?" as an open decision; the data answers it. It still needs clinical sign-off, but as a confirmation rather than a question.

What changes:  two mandatory sequential video proofs with independent status, rather than one combined submit. Death approval continues to apply immediately.

## 4.3   Shifting  —  rework

Already the closest to target. There are two variants, and the branch is priority.

| # | Type | Action | Applies when |
| --- | --- | --- | --- |
| 1 | APPROVAL | Authorisation | always (request variant only) |
| 2 | ACTION_AUTO | Feed Direction | Priority = High |
| 3 | ACTION | Feed Quantity | Priority = High |
| 4 | ACTION | Feed Consumption | Priority = High |
| 5 | MODAL_FORM | Post-Shift Animal Count | Priority = High |
| 6 | ACTION | Upload Shifting Video | Priority = Low |

Production counts confirm the branch: the three feed steps and the post-shift count all sit at 473 occurrences, while the shifting video sits at 434.

What changes:  the app currently models a shifting as one video plus a verification gate. The real workflow is a conditional chain of up to six actions, where a high-priority move pulls in a three-step feed sequence and a post-shift count form. The execute screen must render whatever action list the backend supplies, instead of a fixed single-proof screen.

What must not change:  goats never move between parks; completion with video parks the move at pending verification with nothing relocated and no count moved; animals relocate and counts move only on verifier approval; a rejection bounces back for a re-shoot; missing proof is refused.

One rule conflict to settle before build The legacy system branches feed actions on Priority = High. The confirmed Goat OS rule from 27 July explicitly says "forget high priority" for feed timing. These are different things — projection timing versus which actions appear — and both can stand, but the overlap has to be written down explicitly so the two rules do not drift into each other.

## 4.4   Milk Preparation  —  build

Second-highest volume: 3,848 actions, made up of 218 preparation runs each with four feeding sessions. The subject is a shed tag, not an individual goat.

### Stage 1 — Preparation, same day

| # | Type | Action | Proof required |
| --- | --- | --- | --- |
| 1 | ACTION_AUTO | Milk Direction | none — automatic |
| 2 | MODAL_FORM | Goat Milking Report | form |
| 3 | ACTION_AUTO_VIDEO | Quantity of goat milk to be boiled (litres) | video showing the measured quantity |
| 4 | ACTION_AUTO_VIDEO | Record boiling temperature | video of milk boiled at 72 °C for 1 minute |
| 5 | ACTION_AUTO_VIDEO | Record temperature after milk cools down | video showing milk after cooling |
| 6 | ACTION_AUTO_VIDEO | Quantity of UHT milk | show the number of tetrapaks used |
| 7 | ACTION_AUTO_VIDEO | Add citric acid, mix, and store outside | video showing measured total milk |

Step 7 is a computed instruction — the operator is shown, for example, "Add 594 gms Citric Acid (5.5 gms × 108 litres)". The text itself is generated from the measured volume, so the app must render a backend-computed string and never calculate it on the phone.

Steps 3–5 only appear when goat milk is used — that is a condition evaluated at runtime from an earlier answer.

### Stage 2 — Feeding, next day at 08:00, 12:00, 16:00 and 21:00

Each of the four sessions repeats the same three steps: show clean bottles (video) → mix the milk and fill required bottles (video) → submit the Milk Feeding Report. 872 of each in production = 218 runs × 4 sessions, exactly.

### Quantity configuration

| Shed tag | Millilitres per session | Sessions per day |
| --- | --- | --- |
| K1 | 200 | 4 |
| K2 | 300 | 4 |
| K3 | 200 | 2 |
| Citric acid | 5.5 g per litre of milk | — |

The Milk Feeding Report is a large structured form, filled per shed tag (K0, K1, Kids ICU, K2), capturing for each attempt: the count fed, how many did not drink cow milk, udder milk counts and refusals, ORS counts and refusals, and the number of kids crossing weaning weight with their IDs.

Link into Health:  refusals carry forward for one day, and three carried refusals escalate the kid into the Milk Refusal protocol described in 4.5.

## 4.5   Health  —  build

The clinical surface in the workbook is the Milk Refusal SOP (205 actions), plus Medicine Procurement and a Treatment type that is defined but has no steps authored yet. Milk Refusal is the one with a real branching protocol — and it is the strongest test of the engine, because every branch depends on a previous answer.

### Triage — normal or emergency

| Type | Action | Detail |
| --- | --- | --- |
| QUESTION | Check rectal temperature | Enter °F. Below 100 °F → Emergency Protocol |
| QUESTION | Is the kid standing? | Not standing → Emergency Protocol |

### Normal protocol — escalates with each refusal

| Refusal | Actions |
| --- | --- |
| 1st | Offer ORS 300 ml bottle — "Present gently. If kid refuses, walk away. One missed feed is not a crisis." · Did the kid drink ORS? (note ml) · Any diarrhea or nasal discharge? |
| 2nd | Give RL 200 ml SQ, split across two shoulders, 100 ml each, upload video · Offer ORS 300 ml · Mouth check for sores or redness · Left flank bloating · Perineum diarrhea soiling |
| 3rd | RL 200 ml SQ, then wait 20 minutes · Slosh test — bounce the left flank, is there a sloshing sound? · If no slosh: force feed milk, full volume, 5–10 ml per squeeze over 5–7 minutes · If slosh: force feed ORS 300 ml |
| 4th | RL 200 ml SQ, wait 20 minutes · Force feed milk, full volume, regardless of slosh — non-negotiable · Move to hospital pen with heat source, temperature every 3 hours overnight, supervisor must see this kid |

### Emergency protocol

| # | Action | Detail |
| --- | --- | --- |
| 1 | IP Dextrose 20% at 10 ml/kg body weight | Warm to 39 °C first (hold syringe in warm water 1 minute). Inject 1 cm beside the navel toward the tail, 20G 1-inch needle. Never give under the skin — causes tissue necrosis. |
| 2 | Give RL 200 ml SQ | Separate site from the IP injection. Split across two shoulders. |
| 3 | Warm the kid | Heat lamp or warming box. Warm water bottles wrapped in cloth, never direct on skin. Check temperature every 15 minutes. Target above 98.6 °F. Warm gradually over 30–60 minutes. |
| 4 | Check suckle reflex | Stroke the corner of the mouth. Only proceed to feeding when yes. If no, continue warming and recheck every 15 minutes. |
| 5 | Force feed warm milk slowly | Only when upright and the suckle reflex is present. Take 10 minutes for the full volume. |
| 6 | Move to hospital pen | Do not return to the general pen. Monitor temperature every 2–3 hours. Offer milk at every regular session. |

Discharge back to the general pen:  drinking voluntarily  ·  temperature above 101 °F without external heat for 24 hours  ·  active, mobile and alert.

Why this one drives the engineering This flow must not be built as a static checklist. Whether a kid is in the emergency path, whether the suckle reflex is present, whether the slosh test is positive, whether the kid is in the hospital pen — all of these are produced by answering an earlier step, and each one changes which steps come next. The app has to render whatever the backend says is next. A wrong medical action here is a P0.

Also on the Health page: Medicine Procurement is a simple two-step flow — upload a video of the purchased medicines, then upload the purchase invoice. The Treatment workflow type exists but has no steps authored, so its flow has to be written by the clinical owner before it can be built.

## 4.6   Feed Transport  —  build

Barely exercised in the legacy system — two action rows in total, one template step: upload a Feed Transport video for the session. The subject is a shed.

Honest read:  there is almost no production signal here, so there are two options.

| Option | What it is | Cost | Recommendation |
| --- | --- | --- | --- |
| a | Port as-is — a single video action | Hours | Recommended for the first cut. Faithful to what operators do today. |
| b | Design a real transport flow — pickup confirmation, dispatched quantity, vehicle reference, receipt at destination, discrepancy handling | Days, plus design | Schedule separately. This is net-new product design, not a port, and needs an owner. |

The earlier draft of this document assumed option (b) without flagging that it is net-new work. Recommend shipping (a) by 30 July and taking (b) as its own design item.

## 4.7   Colostrum Feeding  —  build

Currently buried inside the Birth workflow as repeating steps. Production shows the real shape, and it is the key finding for this page.

| Attempt | 1st | 2nd | 3rd | 4th | 5th–7th | 8th | 9th | 10th | 11th | Morning |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Count | 184 | 184 | 182 | 178 | 120 ea. | 108 | 71 | 21 | 2 | 64 |

Colostrum is an open-ended series, not a fixed checklist It is a per-kid series that decays — running to an 11th attempt in real cases, with a separate "Morning Colostrum" alongside. Any design that assumes a fixed session count is wrong against production.

### Session schedule and ownership

| Session | Time | Pre-notify |
| --- | --- | --- |
| Session 1 | 07:00 | 15 minutes |
| Session 2 | 11:00 | 15 minutes |
| Session 3 | 15:00 | 15 minutes |
| Session 4 | 18:30 | 15 minutes |

Ownership is configured per farm and per session — five sessions per farm, each with a named assignee, and ownership hands over mid-day (at one park, sessions 1–2 to one operator, 3–5 to another). The page must resolve the owner from the Goat OS workforce roster and role grants, not from the Slack user IDs in the legacy config.

First colostrum instruction, verbatim from production:  "If suck reflexes are not active use 10 ml syringe for collecting the colostrum and give at least 100 ml. At the beginning of the video, please verify whether the udder contains milk. After giving colostrum give 100ml milk. Is Kid Taking Colostrum?"

Per attempt the operator sees the kid, mother, birth time, shed, owner, due session window and attempt number, records method, quantity, time and the required video, then records the outcome. A refused or partial attempt must create the next attempt or escalate — it must never silently close the obligation.

# 5.  The shared build — why it is the critical path

Six of the seven features are blocked on the same thing, so it gets built once.

Backend — a workflow and action engine: the template, the task instance, and the ordered steps with their own status, schedule, proof, response and verifier. It must support all eight action types, resolve the scheduling rules on Indian business days, evaluate conditions both when the task is created and at runtime from prior answers, and spawn child workflows through the real producers.

Contracts — the task list, task detail with ordered actions, action submit, proof upload, approval verdict, rework and history. All labels, instruction text, option lists and proof requirements are owned by the backend; the app only renders them.

Android — offline-first local storage for tasks and actions, plus one reusable set of renderers covering the eight action types — so adding an eighth workflow is configuration, not a new screen.

Reused as-is — the verification module (approval gate), proof and media (video upload), the counts module (birth, death and shifting canonical state), and notifications (the 15-minute session pre-notify) all already exist and are reused.

# 6.  Roadmap

## Sprint 1 — to Thursday 30 July:  engine plus the three reworks

| Day | Work |
| --- | --- |
| Mon 27 | Freeze the action-type vocabulary, scheduling grammar and condition grammar. Database schema and migration for templates, tasks and actions. Contract for task plus ordered actions. |
| Tue 28 | Backend engine: generate actions from a template, resolve schedules on Indian business days, evaluate conditions, wire child-workflow triggers to the real producers. Register the domain events at both ends. |
| Wed 29 | Android: local storage for tasks and actions with a safe upgrade path, offline queue for action submits, and reusable renderers for the instruction, question, select, form and approval step types. |
| Thu 30 | Rework Birth (mother and kid tracks, scheduled follow-ups), Death (two mandatory videos), Shifting (conditional six-step chain on the existing verification gate). Feed Transport as the single-video port. Full checks, device review, demo. |

Gate 1 exit:  four workflows running on the generic engine, on a real device, proven end to end for replay, offline recovery, rework and app restart.

## Sprint 2 — to Thursday 6 August:  the clinical and milk pages

| Day | Work |
| --- | --- |
| Fri 31 | Colostrum Feeding — open-ended attempt series, session windows, per-session owner from the workforce roster, escalation on refusal. |
| Mon 3 | Milk Preparation stage 1 — the preparation chain, video steps, backend-computed citric acid instruction, and the runtime condition on whether goat milk was used. |
| Tue 4 | Milk Preparation stage 2 — the four next-day feeding sessions, the Milk Feeding Report, per-shed-tag quantities, and refusal carry-forward into the SOP. |
| Wed 5 | Health — the Milk Refusal SOP with its full normal, emergency and discharge branching. Medicine Procurement two-step flow. |
| Thu 6 | Integration, full check suite, rendered review of all seven, demo, and a gap list with named owners and dates. |

Running in parallel and not on the critical path: SOP and clinical publication of the milk, colostrum and Milk Refusal protocol values quoted throughout section 4. Engineering can build against configuration while those values are still held as draft — but the app must not ship them hardcoded.

# 7.  Definition of done

A workflow counts as delivered only when:

its ordered steps carry type, condition, schedule, required proof, owner, due time, status and next action — all owned by the backend, not the app;

conditional steps are evaluated from real prior answers, not rendered as a static checklist;

submissions are safe to retry — a lost connection, a replay or an app restart never creates duplicate business state;

Birth and Death apply on approval; Shifting applies only on verifier approval;

no unpublished medical value has been hardcoded into app behaviour;

the screen clearly distinguishes pending sync, pending approval, rework, completed, cancelled, skipped and blocked;

an end-to-end test exercises the real production path, not a seeded stand-in;

all required checks pass on the delivered build and the test report is published.

# Appendix  —  production volumes, 27 July 2026

| Workflow | Action rows |
| --- | --- |
| Birth | 4,033 |
| Milk Preparation | 3,848 |
| Shifting | 2,581 |
| Milk Refusal SOP | 205 |
| Death | 118 |
| Procurement Transit | 55 |
| Farming Report | 45 |
| Abortion | 4 |
| Feed Transport | 2 |
| Total | 10,891 |

Status split: 8,631 completed · 1,704 scheduled · 322 posted · 135 skipped · 99 cancelled.

Workflow types present in the workbook but outside this slice, which will eventually need the same engine: Feed Packing, Farming Report, Harvesting, Procurement Transit, and a shed Cleaning template of six video steps that has no workflow type assigned yet.